| LAS System | 999 calls -> forms -> map ref lookup -> controller (duplicate removal/district multiplexing) -> division controller (vehicle selection) -> activation box -> radio: 3 minutes, 200 staff |
| --- | --- |
| Problems | Errors (esp. duplication) |
|  | Queues (esp. radio) |
|  | Call-backs laborious |
| Initial Study | £1.5m, 19 months |
|  | Proviso: packaged, no AVLS |
|  | Management forgets provisos |
| Bidding | Firms said proposal unrealistic |
|  | Lowest bidder used for £1m, £700k lower than the next.. |
| Design | 6 month timescale minuted |
|  | No formal meeting program or methodology defined |
|  | No full time user on project |
|  | Systems Options relied on assurances from contractors |
| Implement. | Phase 1 problems: lockup |
|  | Phase 2 problems: blackspots in radio, channel overload at shift change, inability to cope with established practices (taking “wrong” ambulance) |
|  | Management pressure: go live! |
|  | Review asking for volume tests, written implementation strategy, change control and training was ignored |
|  | System put in place in one day without any backup or network managers available |
| Failure | Vehicles lost track of |
|  | Exceptions scrolled off screen |
|  | Incidents held up |
|  | Callbacks increased workload |
|  | Data delays, voice congestion |
|  | Many or none vehicles sent |

| “Software Crisis” | Computer projects had much higher failure risk than others |
| --- | --- |
|  | “Software engineering” coined |
| Why Crisis? | Requirement of perfection |
|  | Conform with systems/ standards outside your control |
|  | Parts interact in more than 3D |
|  | Users demand changes |
|  | Hard to visualise software |
|  | Software is non-repeating |
|  | Requirements change w/ time |
|  | Code becomes complex |
|  | So high rate of bugs found at start and end of lifecycle |
| Big System Problems | Thin spread of domain knowledge in companies |
|  | Communications overhead: hierarchy a good idea? |

| Metrics | Requirements and testing account for 80% of costs |
| --- | --- |
|  | Typically 8KLOC / man year |
| Lessons | Productivity boost comes from using a high level language |
|  | Individuals vary 10x difference |
|  | Brooks’ Law: adding manpower to a late software project makes it later (training + communication costs) |

| Waterfall | Requirements |
| --- | --- |
|  | Specification |
|  | Implementation (unit test) |
|  | Integration (system test) |
|  | Operations / maintenance |
| Validation | Are we building right system? |
|  | Feedback path in first half |
| Verification | Are we building it right? |
|  | Feedback path in second half |
| Advantages | Management easy (milestone) |
|  | Charge for req. changes (even make each stage a contract) |
|  | Conducive to good design |
| Disadvanta. | Applicable only where requirements can be defined in detail (e.g. compiler) |
|  | Reality isn’t like this: iteration is important where tech/law/ requirements/customer environment is changing |
|  | Top down quality betterment may be lost over the lifecycle |
|  | Safety critical, package software have objections |

| Iteration | Determine objectives/alts |
| --- | --- |
|  | Evaluate alts/resolve risks |
|  | Develop and verify prototype |
|  | Plan next phases |
|  | Fixed # of iterations (guarantees termination) |
|  | Increase cost as we spiral |
|  | Only use this on relevant parts of system? (e.g. HCI) |

| Error | Deviation from intended state |
| --- | --- |
| Failure | Non-performance of the system w/ some environment |
| Fault | Error -> fault -> failure |
| Reliability | Probability of failure in period |
| Accident | Unplanned event w/ loss |
| Hazard | Conditions leading to accident |
| Redundancy | Redundant hardware means that software is the failure site |
|  | Multi-version programming leads to programs with correlated errors and misunderstandings |
|  | Redundant outputs can be confusing to human ops. |
| Automation | Computer advises human |
|  | Computer interprets output |
|  | Computer interprets output and input from human |
|  | Human advises computer |
| Testing | Cost per bug rises at later stages -> remove them early |
|  | Change testers regularly |
|  | Due diligence: complying with standards, standard checklist, hire famous consultants… |

| HLLs | LOC goes further (10x) |
| --- | --- |
|  | Code easier to read |
|  | Appropriate abstraction |
|  | Compile time checking |
|  | Portability of code |
|  | Compilers have errors |
|  | Performance may be worse |
|  | Manages incidental complexity |
| Formal Methods | Forces us to be explicit and check designs in detail |
|  | Debate on value for money |
| Tools For Management | Activity charts, critical path analysis, PERT, CASE |
|  | Chief programmers: focused around a 10x productive guy, but team can only do so much |
|  | Egoless programming: code owned by team, not individual |
|  | XP: iteration, user interaction |
|  | LP: code designed for human |
| CMM | Capability Maturity Model |
|  | Keep team together |
|  | Emphasis shift to process |
|  | Repeatable performance |
|  | Debug the process |
| FMEA | Fault mode/effects analysis |
|  | List potential failures and describe the worst case effect |
| Fault Tree | Work backwards systematically from identified hazard to primary events to check which are critical or redundant |
| Change Control | Compatibility check between versions |